## Sheet1
Key | Issue Type | Assignee | Created | Status | Story Points | Component/s | Due Date | Priority | Reporter | Summary | Updated | Sprint | Affects Version/s | Cause Of defect | Labels | Resolution Explanation | Resolved | Epic Link | Time Spent
VECRMSM-1919 | Bug | Mahamood, Rajeez | 2020-09-11 08:24 | COMPLETE | 1 |  | 2020-09-19 | Medium | Kothapalli, Vijaykanth | Suspension alerts link in customer 360 page is not responding. | 2020-10-06 07:44 | VECRM-2020.18 (08/21 - 09/03), VECRM-2020.20(10/02 - 10/15) |  | Unable to Duplicate | VeCRM-Automation | Not an issue | 2020-10-06 07:44 | 441 VECRM 1D design and integration
VECRMSM-1874 | Bug | Sajja, Srinivasa Rao (Sajja) | 2020-09-03 12:38 | COMPLETE | 1 |  |  | Medium | Kothapalli, Vijaykanth | Quicklinks-Documents-File Upload Failing | 2020-09-11 08:19 | VECRM-2020.18 (08/21 - 09/03) |  | Environment/Set-up | VeCRM-Automation, Vecrm_Automation_Defect | config fixed | 2020-09-11 08:19 | 441 VECRM 1D design and integration
VECRMSM-1848 | Bug | Ramanan, Venkat | 2020-08-31 06:31 | COMPLETE | 1 |  |  | Medium | Utpalla, Venkatahareesh | VECRM Issue with regression production testing need to be addressed | 2020-09-01 06:51 | VECRM-2020.18 (08/21 - 09/03) |  | Duplicate | HD_TICKETS | Duplicate | 2020-09-01 06:51 | Application Maintenance - Incident Management
VECRMSM-1847 | Bug | Ramanan, Venkat | 2020-08-31 06:27 | COMPLETE | 2 |  | 2020-09-05 | Medium | Utpalla, Venkatahareesh | Helpdesk ticket number : 2020082713967 (new) OCBC CHI dropped to 69% earlier today. | 2020-09-03 08:43 | VECRM-2020.18 (08/21 - 09/03) |  | Known Issue | HD_TICKETS | User has been made aware of how the calculation is done and it is acknowledged | 2020-09-03 08:43 | Application Maintenance - Incident Management
VECRMSM-1846 | Bug | Ramanan, Venkat | 2020-08-31 06:15 | COMPLETE | 2 |  |  | Medium | Utpalla, Venkatahareesh | VEC¦HD¦ 2020062526366- VECRM issue. | 2020-09-01 07:32 | VECRM-2020.18 (08/21 - 09/03) |  | Known Issue | HD_TICKETS | Full name is the concern of the user in HELM reports and it is fixed already. Acknowledged by the user | 2020-09-01 07:32 | Application Maintenance - Incident Management | 14400
VECRMSM-1819 | Bug | Ramanan, Venkat | 2020-08-26 02:43 | COMPLETE | 2 |  |  | Medium | Utpalla, Venkatahareesh | VEC HD ¦ 2020061312723 ¦ CHI shows incorrect numbers under Pending disconnect Past due under Financial score | 2020-08-27 06:26 | VECRM-2020.18 (08/21 - 09/03) |  | Known Issue | HD_TICKETS | Ticket has been rerouted to EZStatus team. PDPE and disconnect order(red) has difference in score which should be fixed by EZ status team | 2020-08-27 06:26 | Application Maintenance - Incident Management
VECRMSM-1818 | Bug | Ramanan, Venkat | 2020-08-26 00:54 | COMPLETE | 2 |  | 2020-08-28 | Medium | Ramanan, Venkat | VEC HD 2020081733782 - Bill revenue gives different value in VECRM | 2020-08-28 08:39 | VECRM-2020.18 (08/21 - 09/03) |  | Works as Designed | HD_TICKETS | User has no further questions | 2020-08-28 08:39 | Application Maintenance - Incident Management
VECRMSM-1817 | Bug | Ramanan, Venkat | 2020-08-26 00:50 | COMPLETE | 2 |  | 2020-08-29 | Medium | Ramanan, Venkat | VEC HD ¦2020081818054 ¦Unable to view any details for two customers in Vecrm. | 2020-08-31 05:54 | VECRM-2020.18 (08/21 - 09/03) |  | Known Issue | HD_TICKETS | User has been made aware of the scores in the customer page and he has acknowledged. | 2020-08-31 05:54 | Application Maintenance - Incident Management
VECRMSM-1813 | Bug | Francia Huambachano, Manuel | 2020-08-24 20:16 | COMPLETE | 2 |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | Multiple issues were reported by users related to CMPM | 2020-10-14 11:39 | VECRM-2020.18 (08/21 - 09/03), Parking Lot, VECRM-2020.20(09/18 - 10/01) |  | Duplicate | HD_TICKETS | another tkt open | 2020-10-14 11:39 | Application Maintenance - Incident Management
VECRMSM-1801 | Bug | Ramanan, Venkat | 2020-08-24 07:31 | COMPLETE | 2 |  |  | Medium | Ramanan, Venkat | INC004242686 - VEC HD; ETMS Ticket: 2020081331796; User is unable to upload a document in VECRM and need DMS access. | 2020-08-25 02:31 | VECRM-2020.18 (08/21 - 09/03) |  | Known Issue | HD_TICKETS | Access has been provided to the user | 2020-08-25 02:31 | Application Maintenance - Incident Management
VECRMSM-1786 | Bug | Sajja, Srinivasa Rao (Sajja) | 2020-08-20 01:58 | COMPLETE | 1 |  |  | Medium | Kothapalli, Vijaykanth | Projects POD in customer 360 page. | 2020-08-31 04:06 | VECRM-2020.18 (08/21 - 09/03) |  | Code-Bug/Error |  | its fixed in UAT QA2. | 2020-08-31 04:06 | 441 VECRM 1D design and integration
VECRMSM-1768 | Bug | Mahamood, Rajeez | 2020-08-18 21:34 | Ready for Production | 2 |  | 2020-08-29 | Medium | Sajja, Srinivasa Rao (Sajja) | VECRM point to wrong URI from Mega Menu and Header Search | 2020-08-27 13:53 | VECRM-2020.18 (08/21 - 09/03) |  | New Requirement | patch | Added the db script to updated those urls |  | Application Maintenance - Incident Management | 28800
VECRMSM-1735 | Bug | Mahamood, Rajeez | 2020-08-14 12:18 | COMPLETE | 2 |  |  | Very High | Scales, Jennifer | IN chi, there is nothing there for conferencing transactional survey. | 2020-08-25 10:32 | VECRM-2020.18 (08/21 - 09/03) |  | Works as Designed |  | works as designed | 2020-08-25 10:32 | Customer 360 view
VECRMSM-1721 | Bug | Kannan, Sarath | 2020-08-13 09:08 | Ready for Production | 3 |  | 2020-09-05 | Urgent | Reinosa, Boris | Metric click missing customer ID on remarks Incident INC004275277 | 2020-09-03 14:44 | VECRM-2020.18 (08/21 - 09/03) |  | Code-Missing Code | metrics |  |  | Application Maintenance - Incident Management
VECRMSM-1708 | Bug | Francia Huambachano, Manuel | 2020-08-12 07:36 | Ready for Production | 4 |  |  | Medium | Rokde, Supriya | Revenue Realization - Direct link to Revenue Realization is working for users even though they are not added to toggle | 2020-08-24 12:30 | VECRM-2020.18 (08/21 - 09/03) | [5 empty] | Revenue Realization
VECRMSM-1701 | Bug | Kannan, Sarath | 2020-08-12 06:54 | Ready for Production | 1 |  | 2020-08-15 | Medium | Utpalla, Venkatahareesh | Bank account and Credit / Debit card details are not displayed in Manage Payment method Section | 2020-08-28 08:36 | VECRM-2020.18 (08/21 - 09/03) |  | Code-Missing Code | patch
VECRMSM-1672 | Bug | Kannan, Sarath | 2020-08-06 16:40 | Ready for Production | 1 |  | 2020-08-22 | Highest | Sajja, Srinivasa Rao (Sajja) | Trending Graph date change needed - All Score Towers | 2020-08-28 11:29 | VECRM-2020.18 (08/21 - 09/03) |  | Code-Missing Code | patch |  |  | Application Maintenance - Incident Management
VECRMSM-1638 | Bug | Madala, Mahesh | 2020-08-05 09:35 | COMPLETE | 2 |  | 2020-08-22 | Medium | Ramanan, Venkat | INC004170050 - Sorting issue with columns for CHI Drill downs on Dashboard page | 2020-08-28 11:38 | VECRM-2020.17 (08/07 - 08/20, VECRM-2020.18 (08/21 - 09/03) |  | Code-Missing Code | HD_TICKETS, Release, patch | Code-Missing Code | 2020-08-28 11:38 | Application Maintenance - Incident Management
VECRMSM-1606 | Bug | Francia Huambachano, Manuel | 2020-07-30 13:26 | COMPLETE | 2 |  |  | Highest | Luigs, Dawna K | Case Management POD: Showing case count in pod, but when click thru no detail there | 2020-08-25 10:43 | VECRM-2020.18 (08/21 - 09/03) |  | Code-Missing Code |  | code-bug error | 2020-08-25 10:43 | Engage customer through Case Mgmt
VECRMSM-1582 | Bug | Kannan, Sarath | 2020-07-27 16:17 | Ready for Production | 1 | vecrm | 2020-09-05 | Highest | Luigs, Dawna K | Relationship Survey - BI punch out to survey detail has date/dates that are in the future | 2020-09-03 07:25 | VECRM-2020.18 (08/21 - 09/03) |  | Code-Missing Code |  |  |  | Client Health Index
VECRMSM-2013 | Bug | Sajja, Srinivasa Rao (Sajja) | 2020-09-21 03:59 | COMPLETE | 2 |  |  | Medium | Ramanan, Venkat | INC004411726 - VEC¦HD¦2020082618530-VECRM issue. | 2020-09-21 04:00 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Access has been provided to the user | 2020-09-21 04:00 | Application Maintenance - Incident Management
VECRMSM-1964 | Bug | Ramanan, Venkat | 2020-09-18 02:03 | COMPLETE | 2 |  |  | Medium | Ramanan, Venkat | INC004391617 - 2020091603162 - Missing customer in CHI dashboard since today | 2020-09-18 02:05 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | This user has been assigned to the Naspid in POC Tagging but will not be updated in VECRM until Oct 15th. Please have them use the CHI favorite feature until the file is updated. | 2020-09-18 02:05 | Application Maintenance - Incident Management
VECRMSM-1923 | Bug | Ramanan, Venkat | 2020-09-14 04:28 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004362905 - Vec HD¦2020082405051 ¦In VECRM/CHI for the client VOC is not updating. | 2020-09-16 07:00 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue |  | User has been made aware of how VOC score is calculated and he recommnded to close the ticket | 2020-09-16 07:00 | Application Maintenance - Incident Management
VECRMSM-1909 | Bug | Ramanan, Venkat | 2020-09-10 06:30 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004354873 ¦ At Your Service Incident ¦ User unable to search customer | 2020-09-18 08:46 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | User was using previous version and requsted him to search in the new version and it works fine | 2020-09-10 06:32 | Application Maintenance - Incident Management
VECRMSM-1904 | Bug | Reinosa, Boris | 2020-09-09 09:28 | Ready for Production |  |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | Revup API is stuck in loading in QA | 2020-09-17 15:35 | VECRM-2020.19(09/04 - 09/17) | [5 empty] | 441 VECRM 1D design and integration
VECRMSM-1902 | Bug | Kannan, Sarath | 2020-09-09 04:58 | Ready for Production | 1 | vecrm | 2020-09-19 | Medium | Das, Deepak | Issues in VOC score(Relationship survey) | 2020-09-21 01:40 | VECRM-2020.19(09/04 - 09/17) |  | Code-Missing Code | Release |  |  | 441 VECRM 1D design and integration | 7200
VECRMSM-1896 | Bug | Kannan, Sarath | 2020-09-08 02:33 | Ready for Production | 1 |  | 2020-09-19 | Medium | Das, Deepak | Count is not displaying in dropdown for pri1/pri2 drill down in dashboard page | 2020-09-17 15:40 | VECRM-2020.19(09/04 - 09/17) |  | Code-Missing Code | HD_TICKETS |  |  | Application Maintenance - Incident Management
VECRMSM-1895 | Bug | Kannan, Sarath | 2020-09-08 02:30 | Ready for Production | 1 | vecrm | 2020-09-19 | Medium | Das, Deepak | Gch suggestion is broken in 1d accounts page | 2020-09-15 10:44 | VECRM-2020.19(09/04 - 09/17) |  | Code-Missing Code | Release |  |  | 441 VECRM 1D design and integration
VECRMSM-1892 | Bug | Ramanan, Venkat | 2020-09-07 07:16 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | VEC¦HD¦INC004338010 ¦ 2020090406226-VECRM issue. | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Explained the user as to why VOC score is showing as 0% and he has acknowledged to close it. | 2020-09-09 01:48 | Application Maintenance - Incident Management
VECRMSM-1889 | Bug | Ramanan, Venkat | 2020-09-07 07:07 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | VEC HD - 2020090304044 Unable to request access to DMS, getting error | 2020-10-06 09:08 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Access has been provided to the user | 2020-09-07 07:08 | Application Maintenance - Incident Management
VECRMSM-1886 | Bug | Sosa Rios, Daniel | 2020-09-04 12:44 | Ready for Production | 2 |  | 2020-09-19 | Medium | Sosa Rios, Daniel | timeout session in cmpm is not working | 2020-09-17 16:18 | VECRM-2020.19(09/04 - 09/17) | [5 empty] | 441 VECRM Access Optimization
VECRMSM-1856 | Bug | Ramanan, Venkat | 2020-09-01 02:28 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | VECHD ¦ INC004312326 ¦ 2020082818363 ¦ GCH Issue | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Ticket has been rerouted to the GCH team after analysis | 2020-09-04 08:31 | Application Maintenance - Incident Management
VECRMSM-1820 | Bug | Ramanan, Venkat | 2020-08-26 02:59 | COMPLETE | 2 |  | 2020-09-19 | Medium | Utpalla, Venkatahareesh | VECHD ¦ INC004333744 ¦ 2020090120942 ¦ LOADING VECRM WEB | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Had a chat with the user Cole, Linda, she was accessing vecrm from old legacy url, I shared new url and explained how to search for the desired customer in new vecrm 1D, user is able to access vecrm now | 2020-09-07 07:15 | Application Maintenance - Incident Management
VECRMSM-1802 | Bug | Ramanan, Venkat | 2020-08-24 07:33 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004247793 : Heldpesk Ticket Number: 2020081311157 (New) CHI scores are not accurate | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Pri2 tickets are displaying for the user and we requested them to create an ETMS ticket. Other parameters are explained and user achknowledges to close them | 2020-09-14 08:34 | Application Maintenance - Incident Management
VECRMSM-1788 | Bug | Ramanan, Venkat | 2020-08-20 08:46 | Ready for Production |  |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004242785 : KEDB - edit records does not persist current filed data in UI | 2020-09-17 15:57 | VECRM-2020.19(09/04 - 09/17) |  |  | HD_TICKETS |  |  | Application Maintenance - Incident Management