## Sheet1
Key | Issue Type | Assignee | Created | Status | Story Points | Component/s | Due Date | Priority | Reporter | Summary | Updated | Sprint | Affects Version/s | Cause Of defect | Labels | Resolution Explanation | Resolved | Epic Link | Time Spent
VECRMSM-2017 | Bug | Venkateswaran, Hemalata | 2020-09-22 01:47 | COMPLETE | 2 |  | 2020-09-26 | Medium | Venkateswaran, Hemalata | Show ED based on filter selected without afecting the score | 2020-09-25 03:55 | VECRM-2020.19(09/04 - 09/17), VECRM-2020.20(09/18 - 10/01) |  | Code-Bug/Error | patch, vzindia | Handled filtering of ED without affecting scores in query | 2020-09-25 03:55 | CHI Reporting
VECRMSM-2013 | Bug | Sajja, Srinivasa Rao (Sajja) | 2020-09-21 03:59 | COMPLETE | 2 |  |  | Medium | Ramanan, Venkat | INC004411726 - VEC¦HD¦2020082618530-VECRM issue. | 2020-09-21 04:00 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Access has been provided to the user | 2020-09-21 04:00 | Application Maintenance - Incident Management
VECRMSM-1964 | Bug | Ramanan, Venkat | 2020-09-18 02:03 | COMPLETE | 2 |  |  | Medium | Ramanan, Venkat | INC004391617 - 2020091603162 - Missing customer in CHI dashboard since today | 2020-09-18 02:05 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | This user has been assigned to the Naspid in POC Tagging but will not be updated in VECRM until Oct 15th. Please have them use the CHI favorite feature until the file is updated. | 2020-09-18 02:05 | Application Maintenance - Incident Management
VECRMSM-1945 | Bug | Rana, Sahil | 2020-09-16 03:46 | COMPLETE | 1 |  | 2020-09-19 | Medium | Venkateswaran, Hemalata | CHI Reporting performance improvement api showing employee view in manager drilldown | 2020-09-21 04:15 | VECRM-2020.19(09/04 - 09/17) |  | Code-Bug/Error |  | Employee roles were updated in query | 2020-09-21 04:15 |  | 36000
VECRMSM-1930 | Bug | Venkateswaran, Hemalata | 2020-09-15 08:30 | COMPLETE | 1 |  | 2020-09-19 | High | Rokde, Supriya | Sales Contacts - Data not matching legacy contacts | 2020-09-21 04:15 | VECRM-2020.19(09/04 - 09/17) |  | Code-Bug/Error | Release, vzindia | Distinct ph no was retrieved to avoid sql error | 2020-09-21 04:15 | 441 VECRM 1D design and integration
VECRMSM-1929 | Bug | Segabandi, Padma S | 2020-09-14 16:33 | Ready for Production | 5 |  | 2020-09-19 | Medium | Rokde, Supriya | Contacts - NASP list incorrect and data not loading correctly | 2020-09-18 07:39 | VECRM-2020.19(09/04 - 09/17) |  | Code-Bug/Error |  |  |  | 441 VECRM 1D design and integration
VECRMSM-1923 | Bug | Ramanan, Venkat | 2020-09-14 04:28 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004362905 - Vec HD¦2020082405051 ¦In VECRM/CHI for the client VOC is not updating. | 2020-09-16 07:00 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue |  | User has been made aware of how VOC score is calculated and he recommnded to close the ticket | 2020-09-16 07:00 | Application Maintenance - Incident Management
VECRMSM-1913 | Bug | Venkateswaran, Hemalata | 2020-09-10 17:05 | Ready for Production | 1 |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | VECRM Punchout URL from SFDC needs to be corrected | 2020-09-19 03:16 | VECRM-2020.19(09/04 - 09/17) |  |  | Release, vzindia |  |  | 441 VECRM 1D design and integration
VECRMSM-1912 | Bug | Venkateswaran, Hemalata | 2020-09-10 16:38 | COMPLETE | 1 |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | VECRM DMS My Documents Loading issue | 2020-10-14 12:57 | VECRM-2020.19(09/04 - 09/17), VECRM-2020.20(10/02 - 10/15) |  | Code-Missing Code |  | Code change was done | 2020-10-14 12:57 | 441 VECRM 1D design and integration
VECRMSM-1909 | Bug | Ramanan, Venkat | 2020-09-10 06:30 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004354873 ¦ At Your Service Incident ¦ User unable to search customer | 2020-09-18 08:46 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | User was using previous version and requsted him to search in the new version and it works fine | 2020-09-10 06:32 | Application Maintenance - Incident Management
VECRMSM-1905 | Bug | Segabandi, Padma S | 2020-09-09 16:55 | Ready for Production | 3 |  | 2020-09-19 | Medium | Rokde, Supriya | CMPM - NULL Validation when current status is changed to 'Ready for Optima' | 2020-09-23 16:08 | VECRM-2020.19(09/04 - 09/17), VECRM-2020.20(09/18 - 10/01) | [5 empty] | 441 VECRM Access Optimization
VECRMSM-1904 | Bug | Reinosa, Boris | 2020-09-09 09:28 | Ready for Production |  |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | Revup API is stuck in loading in QA | 2020-09-17 15:35 | VECRM-2020.19(09/04 - 09/17) | [5 empty] | 441 VECRM 1D design and integration
VECRMSM-1902 | Bug | Kannan, Sarath | 2020-09-09 04:58 | Ready for Production | 1 | vecrm | 2020-09-19 | Medium | Das, Deepak | Issues in VOC score(Relationship survey) | 2020-09-21 01:40 | VECRM-2020.19(09/04 - 09/17) |  | Code-Missing Code | Release |  |  | 441 VECRM 1D design and integration | 7200
VECRMSM-1896 | Bug | Kannan, Sarath | 2020-09-08 02:33 | Ready for Production | 1 |  | 2020-09-19 | Medium | Das, Deepak | Count is not displaying in dropdown for pri1/pri2 drill down in dashboard page | 2020-09-17 15:40 | VECRM-2020.19(09/04 - 09/17) |  | Code-Missing Code | HD_TICKETS |  |  | Application Maintenance - Incident Management
VECRMSM-1895 | Bug | Kannan, Sarath | 2020-09-08 02:30 | Ready for Production | 1 | vecrm | 2020-09-19 | Medium | Das, Deepak | Gch suggestion is broken in 1d accounts page | 2020-09-15 10:44 | VECRM-2020.19(09/04 - 09/17) |  | Code-Missing Code | Release |  |  | 441 VECRM 1D design and integration
VECRMSM-1892 | Bug | Ramanan, Venkat | 2020-09-07 07:16 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | VEC¦HD¦INC004338010 ¦ 2020090406226-VECRM issue. | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Explained the user as to why VOC score is showing as 0% and he has acknowledged to close it. | 2020-09-09 01:48 | Application Maintenance - Incident Management
VECRMSM-1889 | Bug | Ramanan, Venkat | 2020-09-07 07:07 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | VEC HD - 2020090304044 Unable to request access to DMS, getting error | 2020-10-06 09:08 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Access has been provided to the user | 2020-09-07 07:08 | Application Maintenance - Incident Management
VECRMSM-1888 | Bug | Venkateswaran, Hemalata | 2020-09-04 16:24 | COMPLETE | 1 |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | VECRM DMS ADOM access issue | 2020-10-14 12:58 | VECRM-2020.19(09/04 - 09/17), VECRM-2020.20(10/02 - 10/15) |  | Code-Bug/Error |  | code change was done | 2020-10-14 12:58 | 441 VECRM 1D design and integration
VECRMSM-1886 | Bug | Sosa Rios, Daniel | 2020-09-04 12:44 | Ready for Production | 2 |  | 2020-09-19 | Medium | Sosa Rios, Daniel | timeout session in cmpm is not working | 2020-09-17 16:18 | VECRM-2020.19(09/04 - 09/17) | [5 empty] | 441 VECRM Access Optimization
VECRMSM-1885 | Bug | Sahu, Vivek | 2020-09-04 08:50 | COMPLETE | 1 |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | CHI Issue | 2020-09-21 04:11 | VECRM-2020.19(09/04 - 09/17) |  | Code-Bug/Error | Release, vzindia | decimal case is handled | 2020-09-21 04:11 | 441 VECRM 1D design and integration | 28800
VECRMSM-1872 | Bug | Sahu, Vivek | 2020-09-03 11:35 | COMPLETE | 1 |  | 2020-09-19 | Medium | Venkateswaran, Hemalata | Past MRV link fix in daily alerts in CHI | 2020-09-21 04:11 | VECRM-2020.19(09/04 - 09/17) |  | Code-Bug/Error | vzindia | link is corrected | 2020-09-21 04:11 | Client Health Index | 28800
VECRMSM-1861 | Bug | Segabandi, Padma S | 2020-09-01 11:08 | Ready for Production | 1 |  | 2020-09-19 | Medium | Sajja, Srinivasa Rao (Sajja) | Mega Menu height need to adjust to show all menu items | 2020-09-17 15:43 | VECRM-2020.19(09/04 - 09/17) | [5 empty] | 441 VECRM 1D design and integration
VECRMSM-1857 | Bug | Sahu, Vivek | 2020-09-01 06:56 | COMPLETE | 3 |  | 2020-09-19 | Medium | C, Arthika | Chi Reporting - VP & ED is displayed intermittently in the grid | 2020-09-21 04:10 | VECRM-2020.19(09/04 - 09/17) |  | Code-Bug/Error | Release, vzindia | issue fixed with async calls | 2020-09-21 04:10 | CHI Reporting | 86400
VECRMSM-1856 | Bug | Ramanan, Venkat | 2020-09-01 02:28 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | VECHD ¦ INC004312326 ¦ 2020082818363 ¦ GCH Issue | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Ticket has been rerouted to the GCH team after analysis | 2020-09-04 08:31 | Application Maintenance - Incident Management
VECRMSM-1829 | Bug | Segabandi, Padma S | 2020-08-27 10:41 | Ready for Production | 3 |  | 2020-09-19 | Medium | Rokde, Supriya | CMPM - Add rotating icon when user waits for data load | 2020-09-23 16:07 | VECRM-2020.18 (08/21 - 09/03), VECRM-2020.19(09/04 - 09/17), VECRM-2020.20(09/18 - 10/01) | [5 empty] | 441 VECRM Access Optimization
VECRMSM-1820 | Bug | Ramanan, Venkat | 2020-08-26 02:59 | COMPLETE | 2 |  | 2020-09-19 | Medium | Utpalla, Venkatahareesh | VECHD ¦ INC004333744 ¦ 2020090120942 ¦ LOADING VECRM WEB | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Had a chat with the user Cole, Linda, she was accessing vecrm from old legacy url, I shared new url and explained how to search for the desired customer in new vecrm 1D, user is able to access vecrm now | 2020-09-07 07:15 | Application Maintenance - Incident Management
VECRMSM-1802 | Bug | Ramanan, Venkat | 2020-08-24 07:33 | COMPLETE | 2 |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004247793 : Heldpesk Ticket Number: 2020081311157 (New) CHI scores are not accurate | 2020-09-14 08:43 | VECRM-2020.19(09/04 - 09/17) |  | Known Issue | HD_TICKETS | Pri2 tickets are displaying for the user and we requested them to create an ETMS ticket. Other parameters are explained and user achknowledges to close them | 2020-09-14 08:34 | Application Maintenance - Incident Management
VECRMSM-1788 | Bug | Ramanan, Venkat | 2020-08-20 08:46 | Ready for Production |  |  | 2020-09-19 | Medium | Ramanan, Venkat | INC004242785 : KEDB - edit records does not persist current filed data in UI | 2020-09-17 15:57 | VECRM-2020.19(09/04 - 09/17) |  |  | HD_TICKETS |  |  | Application Maintenance - Incident Management
VECRMSM-1684 | Bug | Segabandi, Padma S | 2020-08-10 01:59 | Cancelled | 4 |  | 2020-09-26 | Medium | Ramanan, Venkat | 2020080418965 , INC004183940 - For address 1137 BRANCHTON RD BOYERS PA 16016 there are only 21 circuits listed in CMPM, when there should be closer to 50 listed | 2020-09-24 16:05 | VECRM-2020.19(09/04 - 09/17), VECRM-2020.20(09/18 - 10/01) |  | Code - Database Change | HD_TICKETS |  | 2020-09-24 16:05 | Application Maintenance - Incident Management
Generated at Wed Nov 18 11:06:50 EST 2020 by Ramanan, Venkat using Jira 8.5.4#805004-sha1:0444eab799707f9ad7b248d69f858774aadfd250.