## Gating Checklist
Reviewed By | Venkat Ramanan B | Release No. & Date | 20.10 & 11/09/2020
Date | 2020-11-09 | EPIC #, Sprint # | VECRMSM-3,118156
S.No | Checkpoints | Response - Mention the name of the tools used whereever applicable | Observation
1 | Is there a traceability of the requirements across all the work products( design, Code, test case etc) ? | Yes | Test case design and also the code is available for all the functionality
2 | Is the prioritized backlog available before the Sprint? | Yes | Backlogs are maintained for each sprint and stories are taken accordingly wrt timelines
3 | Are there any changes to the requirements mid sprint? Is the backlog reprioritized? | Yes | Few changes in the requirements as suggested by the client and the backlog items will be reprioritized after our SCRUM meeting
4 | Are the changes impacting the current functionality? Is Impact analysis performed ?( Validate this based on subtask created ) | Yes
5 | Is there any effort deviation ? Is progress being tracked on daily basis ? (eg.Burn down) | Yes | Burndown chart is produced in the JIRA
6 | Is DOD criteria met for all the requirements? Mention % | Yes | Definition of done is based on acceptance criteria and is always met for all the userstories. - 100%.
7 | Are all the impedepent, dependencies identified and tracked? | Yes | Dependencies if any are called out during the sprint planning and the impedients are tracked in the JIRA
8 | Have all the tests and Peer, Group reviews planned been conducted? | Yes | Reviews are conducted time to time
9 | What is the test coverage and pass % at all the testing Stages.. Mention % | Yes | Test coverage -100% Pass - 100% before pushing the code into production
10 | Are all defects and issues raised through reviews, UT, IT , ST and UAT closed? And Regression testing done? Mention the count of defects at each stage. Calculate DIR, DDR and Defects density. | Yes | All defects are raised after having a review,Regression testing is done through automation on a daily basis Defect Density - 0.029 DDR - 1.3
11 | Is the defect flow defined and internal SLAs established? Is closure tracked through Visual / Kanban boads ? | Yes | Defect life cycle is maintained properly and SLAs ared defined during the SCRUM call, they are regularly tracked
12 | Is RCA done for the defects identified in UT, IT , ST and UAT closed and Prevention acions idetified? | Yes
13 | Are critical/very critical defects which are raised, closed in the cycle? | Yes | Critical issues are addressed immediately
14 | Are security scans done for the code? If so are the blockers fixed? | Yes | HP45, ZAP Scan are the tools used
15 | Does the software satisfy the NFR - performance criteria? | Yes | Avg response time is captured on weekly basis and shared as a report to the business team
16 | Has Retrospective been conducted? If Yes, pls provide Top 3 causes, Types with %ages and Action plan | Yes | Retrospective is conducted within the call at the end of the sprint 1)Business team review comments are addressed 2)Delay in the delivery has been taken care 3)Change in the requirements are adjusted to optimum level
17 | Are relevant documentation/diagrams produced and/or updated ? | Yes | Relevant document related to VECRM are maintained in Gdrive
18 | Does the work product satisfy the work product completion criteria\Acceptance criteria? | Yes | All the user stories have met the acceptance criteria before pusing into the production
19 | Is there are any contractual limitation specified by client for usage of open source component? | NA
20 | Is there are any open source component /software used in coding? | Yes | Angular 5, Node js, Java for Development Selenium protractor, Cucumber for QA testing