## Read Me 1st
Verizon Amber - APPLICATION DEVELOPMENT Metrics Dashboard
Version: | 0.1
Date Published: | 2019-12-27
Last Published By: | Subbu T
Notes: | Deployed
© Infosys Limited 2020.
This metrics dashoard is specifically designed for Verizon Amber Program to be used exclusively by Application Delivery Team.
This document may contain financial, performance and other confidential information including references to contractual obligations.
Not to be circulated beyond Infosys-Verizon Amber Program stakeholders within Infosys.
If you have received this document in error, delete the file permanently (including empty Trash / clean cache / shift+delete email).
Should you have queries or feedback then drop an email to subramaniant@infosys.com.
This dashboard can be used by each application team in a cluster or by each sub-cluster (with application data rolling up) or by cluster (with sub-cluster data rolling up) or at Amber level (with cluster data rolling-up).
For sub-cluster level aggregation, replicate the 'AD Data 2020' sheet for each application and sum the values from each application sheet to 'AD Data 2020'.
Definition Tab = Details definition of each metirc, filter conditions to be used for calculation, and frequency of reporting and the level at which the metric can be reported or aggregated
AD Data 2020 = Fill in the metric value in non-grayed out cells only. Grayed out cells are calculated values and are referenced in AD Dashboard.
AD Dashboard 2020 = Dashboard for the year 2020, month-wise performance shown so that performance can be compared. If Target value is not mentioned then it is very specific to the cluster and to be input by cluster team.
Warning - Do not fill any value in Dashbaord other than the cluster name, portfolio name and application name.

## Definition
ID | Dimension | Category | KPI Name | Description | Unit | Formula | Filter Conditions | Reporting Frequency | Applicability Level | Additional Notes
1 | Efficiency | Agile | Backlog Health | Checks Backlog readiness volume for next 2 sprints - Aims to reduce any requirement readiness issues | Number | Total No. of story points of the refined User stories / (Planned Velocity*2) |  |  | App, Sub-Cluster, Cluster
2 | Efficiency | Agile | Commitment Reliability | Measures teams ability to meet the comittement during Sprint / Release planning | % | Sprint level = (Actual Stories met DOD per Sprint / No of Committed stories)* 100 Release level = (Actual Stories met DOD for the release / No of Committed stories)* 100 |  |  | App, Sub-Cluster, Cluster
3 | SLA | Agile / Iterative Waterfall | Schedule Adherence | % of milestones delivered on time | % | Total deliverables delivered on time / Total deliverables planned for the release * 100% | Milestone moved out by reasons not in Infosys control are counted out | Release | App, Sub-Cluster, Cluster | This metric is part of SLA
4 | SLA | Agile / Iterative Waterfall | Code Change Quality / Emergency Release | Number of emergency change releases made within 5 days of production deployment | Number | Number of emergency change releases made within 5 days of production deployment | Issues are attributable to Infosys delivery | Release | App, Sub-Cluster, Cluster | This metric is part of SLA
5 | Demand | Agile / Iterative Waterfall | Demand Supply Index | % of requirements Infosys could commit without any capacity issues | % | Number of requirements or Task Orders or user stories committed for the requested date or release / Total requirements or Task Orders or user stories requested in the month * 100% | If any requirement or task order for which Infosys has requested a later release date due to capcity issues then do not count those in the numerator. Also do not count user stories that were not committed due to not being ready | Release | App, Sub-Cluster, Cluster
6 | Demand | Agile | Change Requests % | % of changes requested to stories that were already in development once the release development cycle has begun | % | Total number of change requests across all stories in development / Total number of stories in development * 100% |  | Release | App, Sub-Cluster, Cluster | If two different changes are requested on the same story then it has to be counted as two changes regardless of whether they arrived at same time.
7 | Efficiency | Agile / Iterative Waterfall | Estimation Accuracy over/(under) | % of effort deviation from estimate | % | 100% - (Total effort spent on all requirements delivered in the release including CRs / Total effort estimated for the requirements including CRs * 100%) |  | Release | App, Sub-Cluster, Cluster | Negative % means underestimated (actual is high), Positive % means overestimated (actual is lower)
8 | Efficiency | Agile / Iterative Waterfall | Productivity | Number of size units delivered per person month effort | Number | Number of story points delivered for the release including CRs / Actual effort in person month spent on the deliverables including CRs |  | Release | App, Sub-Cluster, Cluster
9 | Efficiency | Agile | Planned Velocity | Total No. of Story points to be committed by the team per sprint | Number | Total size units or story points planned for the release / Total sprints in the release Planned |  |  | App, Sub-Cluster, Cluster
10 | Efficiency | Agile | Actual Velocity | Average size units delivered per sprint for the release | Number | Total size units or story points delivered for the release / Total sprints in the release |  | Release | App, Sub-Cluster, Cluster
11 | Efficiency | Agile | On Time Requirements Readiness % | % of user stories that meet all criteria in Definition of Ready to start development on time | % | Total number of stories that met all criteria in Definition of Ready before start of sprint / Total number of stories planned for the release * 100% |  | Release | App, Sub-Cluster, Cluster | Definition of Ready for development start should be defined by the dev team and agreed with client stakeholders. This DoR is different from DoR criteria that would be applied for the story to be ready for deployment.
12 | Efficiency | Agile | User Story Acceptance | User Stories acceptance rate by PO post Sprint completion | % | User Story Accepted / User Stories met DOD
13 | Efficiency | Agile | Scrum Process Index | Measures the discipline of conducting Agile Ceremonies and maintaining the relevent artifacts | Number | All the 5 ceremonies are practiced and respective key artifacts (PB, RB, RP, DOR, DOD, SB, SBD chart, Impediments log, Retro action log, Velocity Trend) are maintained
14 | Qualtiy | Agile / Iterative Waterfall | Code Coverage | Measure Unit testing Coverage | % | Measure Unit testing Coverage either through automated tool or any manual mechanism
15 | Efficiency | Agile | Velocity Gain | Continous monitoring of Velocity performance in terms of trend charts | Chart | Velocity Trend showing Increase
16 | Qualtiy | Agile | Defect Backlog | No. of defect carry forwarded to next Sprint without fixing | % | ((Total No. of Defects + Carry forward defects – No. of Closed Defects) / Total No. of Sprint Defects)*100
17 | Efficiency | Agile / Iterative Waterfall | Avg Dev Time to Resolve Defects (QA) | Average time taken for Dev Team to resolve defects in QA | Hours | Total time of all valid QA defects in Dev queue / Total number of valid defects resolved in QA phase | Defect close date = Reporting period Defect root cause = Application code/config, Build Kit/Instructions Defect assigned to = Infosys DEV team at least once Defects where state is not = "working as defined“, “clarifications”, “duplicate”, “can not replicate”, “production problem”, “Insufficient information”, “de-scoped” or "as designed“ Defect application = Infosys scope | Release | App, Sub-Cluster, Cluster | QA is after UT but before UAT - Module Test, System Test, Integration Test, Performance Test, Regression Test, Load Test
18 | Efficiency | Agile / Iterative Waterfall | Avg Dev Time to Resolve Defects (UAT) | Average time taken for Dev Team to resolve defects in UAT | Hours | Total time of all valid UAT defects in Dev queue / Total number of valid defects resolved in UAT phase |  | Release | App, Sub-Cluster, Cluster
19 | Quality | Agile / Iterative Waterfall | Critical Incidents Caused by Release | Number of critical incidents caused by the release that was deployed | Number | Number of critical incidents caused by the release that was deployed |  | Release | App, Sub-Cluster, Cluster | Critical incident may not necessarily result in emergency code change hence this metric complements the SLA metric
20 | Quality | Agile / Iterative Waterfall | Defect Injection Rate - Requirements | % of defects injected during requirements phase | % | Total number of defects attributable to requirements / Total number of valid defects found in all phases after requirements including production * 100% |  | Release | App, Sub-Cluster, Cluster
21 | Quality | Agile / Iterative Waterfall | Defect Injection Rate - Design | % of defects injected during design phase | % | Total number of defects attributable to design phase / Total number of valid defects found in all phases after design including production * 100% | High level design and detailed design included | Release | App, Sub-Cluster, Cluster
22 | Quality | Agile / Iterative Waterfall | Defect Injection Rate - Coding | % of defects injected during coding phase | % | Total number of defects attributable to coding / Total number of valid defects found in all phases after coding including UT, QA, UAT and production * 100% |  | Release | App, Sub-Cluster, Cluster
23 | Quality | Agile / Iterative Waterfall | Defect Density by Effort | Number of defects per Person day | Ratio | Total no. of Internal defects / Overall Sprint effort in Person days
24 | Quality | Agile / Iterative Waterfall | Defect Removal Effienciency | Development Teams ability to remove the defects in the Release / Sprint | % | Total No. of Internal Defects identified by Dev team in Design & Code Review, Unit testing / (Total No. of Internal Defects + Total QA defect + Total No. of UAT / Client Reported defects)
25 | Quality | Agile / Iterative Waterfall | Defect Density (QA + UAT) Per Unit Size | Number of defects per story point size in QA and UAT phases | Ratio | Total number of all valid defects in QA and UAT / Total size of deliverables |  | Release | App, Sub-Cluster, Cluster
26 | Quality | Agile / Iterative Waterfall | Defect Density (P1 and P2 QA + UAT) Per Unit Size | Number of P1 and P2 defects per story point size in QA and UAT phases | Ratio | Total number of valid P1 and P2 defects in QA and UAT / Total size of deliverables | Only P1 and P2 defects | Release | App, Sub-Cluster, Cluster
27 | Quality | Agile / Iterative Waterfall | Escaped Defects Density (All) Per Unit Size | Number of defects found in production within 30 days of deployment that were not caught during SDLC phases per story point size | Ratio | Number of defects found in production within 30 days of release deployment / Total size of deliverables | All production problems P1 to P4 attributable to Infosys | Release | App, Sub-Cluster, Cluster
28 | Quality | Agile / Iterative Waterfall | Escaped Defects Density (P1 & P2) Per Unit Size | Number of P1 and P2 defects found in production within 30 days of deployment that were not caught during SDLC phases per story point size | Number | Number of P1 and P2 defects found in production within 30 days of release deployment / Total size of deliverables | Production problems of type P1 and P2, attributable to Infosys | Release | App, Sub-Cluster, Cluster
29 | Quality | Agile / Iterative Waterfall | Rework % | % of effort spent on rework due to quality issues | % | Effort spent in person month on rework due to quality issues / Total effort in person month spent on deliverables * 100% |  | Release | App, Sub-Cluster, Cluster
30 | Testing | Agile / Iterative Waterfall | Test Automation (UT) % | % if test cases that were automated and executed in Unit Testing | % | Total Number of Automated Unit Test Cases / Total Number of Unit Test Cases * 100% |  | Release | App, Sub-Cluster, Cluster
31 | Testing | Agile / Iterative Waterfall | Test Automation (Regression) % | % if test cases that were automated and executed in Regression Testing | % | Total Number of Automated Regression Test Cases / Total Number of Regression Test Cases * 100% |  | Release | App, Sub-Cluster, Cluster
32 | Testing | Agile / Iterative Waterfall | Test Effectiveness | Effectiveness of testing before delivering the code to UAT | % | Total number of valid defects caught in Design, UT and QA phase / Total valid defects caught in Design, UT, QA, UAT and in Production within first 30 days * 100% |  | Release | App, Sub-Cluster, Cluster
33 | Testing | Agile / Iterative Waterfall | QA Team Effectiveness | Effectiveness of QA team in catching only valid defects in 1st attempt | % | Total number of valid defects caught in QA phase / Total defects (valid and not valid) defects caught in QA phase * 100% | Defects not valid are "working as defined“, “clarifications”, “duplicate”, “can not replicate”, “Insufficient information”, "as designed“ | Release | App, Sub-Cluster, Cluster | Applicable only if there is a separate QA team that executes tests after UT and before UAT

## AD Dashboard 2020
Verizon Amber - AD Metrics Dashboard |  | >>>>>> | >>>>>> | Cluster: |  | Portfolio: | <Portfolio Name> |  | App Name: | <Application Name> |  |  |  |  | Do not update any value directly on the dashboard
Dimension | Application Development Metric | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | Target
SLA | Schedule Adherence | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 100% | 100% | 100% |  |  |  | 100%
| Code Change Quality / Emergency Release | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | 0
Demand | Demand Supply Index | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 100% | 100% | 100% |  |  |  | 100%
| Change Requests % | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 100% | 100% | 100% |  |  |  | <5%
Efficiency | Estimation Accuracy over/(under) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% |  |  |  | +/- 2%
| Productivity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 |  |  |  | TBD
| Velocity | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 |  |  |  | TBD
| On Time Requirements Readiness % | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 100% | 100% | 100% |  |  |  | 100%
| Avg Dev Time to Resolve Defects (QA) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0.44444 | 0.48544 | 0.46667 | 0.50794 |  |  |  | <24 Hours
| Avg Dev Time to Resolve Defects (UAT) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5.2444 | 6.0874 | 3.3333 | 3.4921 |  |  |  | <24 Hours
Quality | Critical Incidents Caused By Release | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | 0
| Defect Injection Rate - Requirements | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% |  |  |  | TBD
| Defect Injection Rate - Design | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% |  |  |  | TBD
| Defect Injection Rate - Coding | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 8.242% | 7.177% | 3.947% | 5.469% |  |  |  | TBD
| Defect Density (QA + UAT) Per Unit Size | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | TBD
| Defect Density (P1 and P2 QA + UAT) Per Unit Size | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | TBD
| Escaped Defects Density (All Defects) Per Unit Size | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | 0
| Escaped Defects Density (P1 & P2) Per Unit Size | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | 0
| Rework % | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% |  |  |  | <2%
Testing | Test Automation (UT) % | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [7 empty] | 95%
| Test Automation (Regression) % | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 43.75% | 45.12% | 58.82% | 70.53% |  |  |  | 95%
| Test Effectiveness | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 50.55% | 50.72% | 50.66% | 50.78% |  |  |  | 100%
| QA Team Effectiveness | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100% | 100% | 100% | 100% |  |  |  | 100%

## AD Data 2020 - Raw Data
Metric Calculation From Data | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
Total requirements or Task Orders or user stories requested by client in the month or release | 63 | 67 | 41 | 37
Number of requirements or Task Orders or user stories committed for the requested date or release | 63 | 67 | 41 | 37
Demand Supply Index | 100% | 100% | 100% | 100%
Total number of requiremements or task orders or user stories committed for the release | 63 | 67 | 41 | 37
Total number of requiremements or task orders or user stories received change during release | 63 | 67 | 41 | 37
Change Requests % | 100% | 100% | 100% | 100%
Total effort in person months estimated for delivered requirements / user stories excluding CRs | 1395.5 | 1581.65 | 470 | 420
Total effort in person months estimated for CRs | 0 | 0 | 0 | 0
Total effort in person months spent on delivered requirements / user stories excluding CRs | 1395.5 | 1581.65 | 470 | 420
Total effort in person months spent on CRs | 0 | 0 | 0 | 0
Estimation Accuracy over/(under) | 0% | 0% | 0% | 0%
Number of story points or size units planned for the release including CRs | 0 | 0 | 0 | 0
Number of story points or size units delivered in the release including CRs | 0 | 0 | 0 | 0
Total No. of Story Points of refined user stories | 222 | 294 | 104 | 89
Number of Sprints in the release | 2 | 2 | 2 | 2
Actual Stories met DOD per Sprint | 63 | 67 | 41 | 37
Actual Stories met DOD for the release | 63 | 67 | 41 | 37
Productivity | 0 | 0 | 0 | 0
Velocity | 0 | 0 | 0 | 0
Total number of requirements or user stories planned for the release | 63 | 67 | 41 | 37
Total number of requirements or user stories ready as per Definition of Ready at start of sprint | 63 | 67 | 41 | 37
Total number of requirements or user stories delivered on time for the release | 63 | 67 | 41 | 37
Total User Stories met DOD | 63 | 67 | 41 | 37
Total User Story Accepted | 63 | 67 | 41 | 37
Schedule Adherence | 100% | 100% | 100% | 100%
On Time Requirements Readiness % | 100% | 100% | 100% | 100%
Total valid defects during design phase | 0 | 0 | 0 | 0
Total valid UT defects | 2 | 3 | 2 | 2
Total valid QA defects (after UT but before UAT) | 90 | 103 | 75 | 63
Total valid UAT defects | 90 | 103 | 75 | 63
Total valid defects in Production within first 30 days of deployment | 0 | 0 | 0 | 0
Total valid defects caused by Requirements | 0 | 0 | 0 | 0
Total valid defects caused by Design | 0 | 0 | 0 | 0
Total valid defects caused by Coding | 15 | 15 | 6 | 7
Total valid P1 and P2 defects in QA (after UT but before UAT) | 0 | 0 | 0 | 0
Total valid P1 and P2 defects in UAT | 10 | 13 | 16 | 13
Total valid P1 and P2 defects in production within 30 days of deployment | 0 | 0 | 0 | 0
Total time in hours in Dev queue for all valid QA defects (after UT but before UAT) | 40 | 50 | 35 | 32
Carry forward defects | 0 | 0 | 0 | 0
No. of Closed Defects | 90 | 103 | 75 | 63
Total time in hours in Dev queue for all valid UAT defects | 472 | 627 | 250 | 220
Effort in person months spent on rework due to quality issues | 0 | 0 | 0 | 0
Avg Dev Time to Resolve Defects (QA) | 0.44444 | 0.48544 | 0.46667 | 0.50794
Avg Dev Time to Resolve Defects (UAT) | 5.2444 | 6.0874 | 3.3333 | 3.4921
Defect Injection Rate - Requirements | 0 | 0 | 0 | 0
Defect Injection Rate - Design | 0 | 0 | 0 | 0
Defect Injection Rate - Coding | 0.082418 | 0.07177 | 0.039474 | 0.054688
Defect Density (QA + UAT) Per Unit Size
Defect Density (P1 and P2 QA + UAT) Per Unit Size
Escaped Defects Density (All Defects UAT and Prod) Per Unit Size
Escaped Defects Density (P1 & P2 UAT and Prod) Per Unit Size
Rework % | 0% | 0% | 0% | 0%
Total number of tests in UT (automated and manual) executed in the release | 0 | 0 | 0 | 0
Number of automated tests in UT executed in the release | 0 | 0 | 0 | 0
Test Automation (UT) %
Total number of tests in Regression Suite (automated and manual) | 400 | 410 | 425 | 475
Number of automated tests in Regression Suite | 175 | 185 | 250 | 335
Test Automation (Regression) % | 43.75% | 45.12% | 58.82% | 70.53%
Test Effectiveness | 50.55% | 50.72% | 50.66% | 50.78%
Total not valid QA defects (after UT but before UAT) | 0 | 0 | 0 | 0
QA Team Effectiveness | 100% | 100% | 100% | 100%
Number of emergency releases within 7 days of production deployment | 0 | 0 | 0 | 0
Number of Critical Incidents Caused by Release | 0 | 0 | 0 | 0